## Cover
SYSTEM TEST CASE ¦ SMARTPARKING
Project Name | SmartParking |  |  | Creator | QA Team
Project Code | SPARK |  |  | Reviewer / Approver | Pending Leader review
Document Code | SPARK_User_Master_TestCases_v1.0 |  |  | Issue Date | 2026-10-28
Service / ownership | User |  |  | Version | 1.1 REVIEW
Record of change
Effective Date | Version | Change Item | A,D,M | Change description | Reference
2026-10-28 | 1.0 | Create shared master | A | One persistent workbook per service; append QA tests over time. | Mentor TestTeam_UAT.xlsx
2026-10-28 | 1.1 | Migrate SPARK177 + PR9 | A | 17 User PASS + 15 planned; unit and prior runs indexed | PR9/177 historical source ZIP
Quy tắc: ghi theo service gốc gọi đầu tiên; không nhân đôi test liên service.
Không thay thế dữ liệu cũ khi cập nhật task mới; bảo toàn lịch sử test và baseline.
Chưa được Leader phê duyệt. Đối chiếu docs repo trước khi commit.

## Test Report
TEST REPORT ¦ USER
Project Name | SmartParking |  |  | Creator | QA Team
Project Code | SPARK |  |  | Reviewer | Pending
Document Code | SPARK_User_Master_TestCases_v1.0 |  |  | Last updated | 2026-10-28
Notes | Master test cases; Unit/DI assertions are reported in Word only. |  |  | Historical SPARK-177 (multiple baselines) + PR9 current 05e2976d; Unit tests are separate.
No | Module code | Pass | Fail | Untested | N/A | Number of test cases | % Passed of tests | Blocked
1 | PR9_Owner_E2E | 10 | 0 | 0 | 0 | 10 | 100% | 0
2 | PR9_Auth_UI | 7 | 0 | 0 | 0 | 7 | 100% | 0
3 | SP177_Planned_QA | 0 | 0 | 15 | 0 | 15 | 0% | 0
| Sub total | 17 | 0 | 15 | 0 | 32 | 53.12% | 0
QA execution coverage | 53.12%
Status / sign-off | PR9 Owner positive E2E/UI targeted PASS on 05e2976d; SPARK-177 planned scenarios NOT EXECUTED. QA overall not signed off.
Notes | Blocked is shown separately; Unit Tests do NOT inflate QA case counts.
Source | PR9 Word/Excel 2026-10-22; SPARK177 historical DRAFT and Gap Matrix. Historical run totals kept separately.
UNIT TEST (reference only) | Passed | Failed | Skipped | Execution
SPARK-177 / Fix2FA | 73 | 0 | 26 | 99 total on 19/10/2026; tests skipped; independent review pending
PR9 / 05e2976d | 167 | 0 | 0 | Developer .NET test rerun / 22/10/2026; different SHA
Do not add Unit Tests above to QA Pass column.

## Test Case List
TEST CASE LIST ¦ USER
Project Name |  | SmartParking
Project Code |  | SPARK
Test Environment Setup Description |  | Windows 11; .NET 10 / QA mock; PostgreSQL 16 (only where verified)
No | Function Name | Sheet Name | Description | Pre-Condition
1 | PR9_Owner_E2E | PR9_Owner_E2E | 10 Owner onboarding positive E2E checks, UserService-root | PR9 QA account; local SMTP, User/Facility/Reservation APIs
2 | PR9_Auth_UI | PR9_Auth_UI | 7 additional Admin/Owner/Sign-up UI checks | Current 05e2976d UI; QA user role
3 | SP177_Planned_QA | SP177_Planned_QA | 15 SPARK-177 pending test scenarios; not executed | Approved auth requirements; safe auth fixtures

## Migration Queue
HISTORICAL TEST INTAKE ¦ USER
Historical summaries below are NOT added to current QA Pass/Fail totals until original case evidence is reconciled.
Source task / PR | Scope | Prior outcome summary | Required evidence / actions | Migration status
SPARK-177 | Login/Logout API Testing + UAT | 15 planned QA test cases imported as UNTESTED; 19 demo PASS, 9 Fix2FA PASS, 5 negative smoke PASS kept as historical runs only; xUnit 73/0/26. | Historical runs have no row-level raw execution in ZIP; do not mark baseline current PASS. MFA 500 unresolved cause; Newman/UAT incomplete. | 15 PLANNED CASES + HISTORY INDEXED
PR #9 | Owner onboarding / Fix2FA QA | 17 detailed User-root PR9 positive/UI cases imported (10 Owner E2E + 7 Admin/Auth UI); 167 xUnit pass separate. Facility UI 2 cases provisional. | PR9 SHA 05e2976d; QA candidate tasks SPARK-181 (registration) / SPARK-197 (approval), mapped provisionally per case; confirm against Jira scope. SMTP Gmail 535 was environment/account, not proven product bug. | 17 USER CASES IMPORTED; FACILITY OWNER TBC

## PR9_Owner_E2E
SMART PARKING ¦ PR9_Owner_E2E
Module Code | PR9_Owner_E2E
Test requirement | PR #9 · QA key TBD
Reference Document | UserService-root Owner registration workflow (10 linked checks), baseline 05e2976d; email via UserService worker.
% Passed of tests | Pass | Fail | Untested | N/A | Number of test cases | Blocked
100% | 10 | 0 | 0 | 0 | 10 | 0
Nguồn: tài liệu gốc trong Historical ZIP. Tổng hợp theo nhiều commit; không suy diễn kết quả ở HEAD mới.
ID | Test Case Description | Test Case Procedure | Expected Results | Inter-test case Dependence | Result | Test date | Tester | Number of tests | Passed | % Passed | Note / Actual | Testing Jira | Baseline commit | Evidence / source | Scenario type
[PR9-E2E-01] | E2E / New Owner | Sign Up > Business; tạo tài khoản test | Chấp nhận đăng ký hợp lệ | QA email alias chưa tồn tại, số thử không trùng | Pass | 2026-10-22 | QA Tester | 1 | 1 | 100% | Chuyển sang thiết lập bãi đỗ, không còn CONTACT_EXISTS Test positive; chỉ dùng dữ liệu QA | SPARK-181 (provisional PR9 mapping; verify scope) | 05e2976d (short SHA, source-reported) | EV-E2E-01 · PR9_QA_Traceability_Final.xlsx TEST_CASES; screenshot index in PR9_QA_Final_Report.docx | UserService origin / FE owner-onboarding / Admin auth (UI evidence)
[PR9-E2E-02] | E2E / Lot setup | Outdoor Lot; Structure; Devices; Pricing & Policy; Confirm; Save | Lot được lưu, chuyển sang verify email | Đăng ký Owner QA đã tạo bước đầu | Pass | 2026-10-22 | QA Tester | 1 | 1 | 100% | Thông báo lot setup saved và form verification xuất hiện Lot name PR9 QA SMTP Test Lot, 20 planned slots | SPARK-181 (provisional PR9 mapping; verify scope) | 05e2976d (short SHA, source-reported) | EV-E2E-01 · PR9_QA_Traceability_Final.xlsx TEST_CASES; screenshot index in PR9_QA_Final_Report.docx | UserService origin / FE owner-onboarding / Admin auth (UI evidence)
[PR9-E2E-03] | E2E / Real OTP email | Submit setup; mở Gmail của người nhận | OTP thật vào Inbox | UserService SMTP Gmail qtang... & recipient QA | Pass | 2026-10-22 | QA Tester | 1 | 1 | 100% | SmartPark verification nhận lúc 17:30, từ Gmail thay thế OTP đã che trong Word; không lưu mã | SPARK-181 (provisional PR9 mapping; verify scope) | 05e2976d (short SHA, source-reported) | EV-E2E-02 · PR9_QA_Traceability_Final.xlsx TEST_CASES; screenshot index in PR9_QA_Final_Report.docx | UserService origin / FE owner-onboarding / Admin auth (UI evidence)
[PR9-E2E-04] | E2E / OTP verify | Nhập OTP trong Verification UI và Verify | Email verified; application submitted | Có OTP Gmail thật còn hiệu lực | Pass | 2026-10-22 | QA Tester | 1 | 1 | 100% | Trang Application Submitted; under Admin review Positive OTP; negative/expired chưa test mới | SPARK-181 (provisional PR9 mapping; verify scope) | 05e2976d (short SHA, source-reported) | EV-E2E-03 · PR9_QA_Traceability_Final.xlsx TEST_CASES; screenshot index in PR9_QA_Final_Report.docx | UserService origin / FE owner-onboarding / Admin auth (UI evidence)
[PR9-E2E-05] | E2E / Admin pending | Owner Partnership Applications > Refresh | Hồ sơ verified xuất hiện Pending | Admin QA signed in | Pass | 2026-10-22 | QA Tester | 1 | 1 | 100% | Pending Review (1); contact Verified, lot chính xác Không duyệt hồ sơ khác | SPARK-197 (provisional PR9 mapping; verify scope) | 05e2976d (short SHA, source-reported) | EV-E2E-04 · PR9_QA_Traceability_Final.xlsx TEST_CASES; screenshot index in PR9_QA_Final_Report.docx | UserService origin / FE owner-onboarding / Admin auth (UI evidence)
[PR9-E2E-06] | E2E / Approve | Nhập review note QA; click Approve một lần | Owner chuyển APPROVED | Hồ sơ QA đang Pending Review | Pass | 2026-10-22 | QA Tester | 1 | 1 | 100% | Mục Previously Reviewed hiển thị APPROVED Không lặp thao tác; approval 1 lần | SPARK-197 (provisional PR9 mapping; verify scope) | 05e2976d (short SHA, source-reported) | EV-E2E-05 · PR9_QA_Traceability_Final.xlsx TEST_CASES; screenshot index in PR9_QA_Final_Report.docx | UserService origin / FE owner-onboarding / Admin auth (UI evidence)
[PR9-E2E-07] | E2E / Workflow delivery | Refresh Admin applications; xem Notification status | Pending → Sent | Owner approved; UserService background worker chạy | Pass | 2026-10-22 | QA Tester | 1 | 1 | 100% | Dòng hồ sơ mới từ pending chuyển sent Status lưu của workflow; cần email nhận để chốt | SPARK-197 (provisional PR9 mapping; verify scope) | 05e2976d (short SHA, source-reported) | EV-E2E-05 · PR9_QA_Traceability_Final.xlsx TEST_CASES; screenshot index in PR9_QA_Final_Report.docx | UserService origin / FE owner-onboarding / Admin auth (UI evidence)
[PR9-E2E-08] | E2E / Approval email | Kiểm tra Gmail nhận | Nhận email kết quả APPROVED | Notification sent; người nhận có Inbox | Pass | 2026-10-22 | QA Tester | 1 | 1 | 100% | SmartPark application decision 17:33; 'Your application is approved.' Delivery tới Inbox xác minh bằng ảnh | SPARK-197 (provisional PR9 mapping; verify scope) | 05e2976d (short SHA, source-reported) | EV-E2E-06 · PR9_QA_Traceability_Final.xlsx TEST_CASES; screenshot index in PR9_QA_Final_Report.docx | UserService origin / FE owner-onboarding / Admin auth (UI evidence)
[PR9-E2E-09] | E2E / Owner sign-in | Sign In bằng account QA | Cho truy cập Owner Dashboard | Owner QA mới APPROVED | Pass | 2026-10-22 | QA Tester | 1 | 1 | 100% | Owner Overview hiển thị tài khoản QA Không công bố mật khẩu | SPARK-181 (provisional PR9 mapping; verify scope) | 05e2976d (short SHA, source-reported) | EV-E2E-07 · PR9_QA_Traceability_Final.xlsx TEST_CASES; screenshot index in PR9_QA_Final_Report.docx | UserService origin / FE owner-onboarding / Admin auth (UI evidence)
[PR9-E2E-10] | E2E / Assigned site | Mở Site filter, chọn PR9 QA SMTP Test Lot | Chỉ site của Owner được hiển thị | Owner đã đăng nhập | Pass | 2026-10-22 | QA Tester | 1 | 1 | 100% | Filtered site view; site có trong dropdown Capacity 0 phụ thuộc physical layout | SPARK-181 (provisional PR9 mapping; verify scope) | 05e2976d (short SHA, source-reported) | EV-E2E-08 · PR9_QA_Traceability_Final.xlsx TEST_CASES; screenshot index in PR9_QA_Final_Report.docx | UserService origin / FE owner-onboarding / Admin auth (UI evidence)

## PR9_Auth_UI
SMART PARKING ¦ PR9_Auth_UI
Module Code | PR9_Auth_UI
Test requirement | PR #9 · QA key TBD
Reference Document | 7 independent UI checks (admin/owner authentication, sign-up UI and validation); no backend token revocation inferred.
% Passed of tests | Pass | Fail | Untested | N/A | Number of test cases | Blocked
100% | 7 | 0 | 0 | 0 | 7 | 0
Nguồn: tài liệu gốc trong Historical ZIP. Tổng hợp theo nhiều commit; không suy diễn kết quả ở HEAD mới.
ID | Test Case Description | Test Case Procedure | Expected Results | Inter-test case Dependence | Result | Test date | Tester | Number of tests | Passed | % Passed | Note / Actual | Testing Jira | Baseline commit | Evidence / source | Scenario type
[PR9-R22-04] | Admin login | Sign In Admin | Authenticated admin UI | Admin existing; FE 5173 | Pass | 2026-10-22 | QA Tester | 1 | 1 | 100% | Admin role menu and Applications visible Không lặp đăng ký tài khoản | SPARK-197 (provisional PR9 mapping; verify scope) | 05e2976d (short SHA, source-reported) | EV-ADMIN-01 · PR9_QA_Traceability_Final.xlsx TEST_CASES; screenshot index in PR9_QA_Final_Report.docx | UserService origin / FE owner-onboarding / Admin auth (UI evidence)
[PR9-R22-05] | Approval display | Admin > Owner Partnership Applications | Existing APPROVED owner visible | Owner đã được approve trong dữ liệu cũ | Pass | 2026-10-22 | QA Tester | 1 | 1 | 100% | QA Test Parking APPROVED / notification sent Display of persisted mock-send; not Gmail evidence | SPARK-197 (provisional PR9 mapping; verify scope) | 05e2976d (short SHA, source-reported) | EV-ADMIN-OLD · PR9_QA_Traceability_Final.xlsx TEST_CASES; screenshot index in PR9_QA_Final_Report.docx | UserService origin / FE owner-onboarding / Admin auth (UI evidence)
[PR9-R22-06] | Owner login | Sign In Owner | Owner role access | Owner QA Tester existing | Pass | 2026-10-22 | QA Tester | 1 | 1 | 100% | Owner authenticated / QA Tester displayed - | SPARK-181 (provisional PR9 mapping; verify scope) | 05e2976d (short SHA, source-reported) | EV-OWNER-OLD · PR9_QA_Traceability_Final.xlsx TEST_CASES; screenshot index in PR9_QA_Final_Report.docx | UserService origin / FE owner-onboarding / Admin auth (UI evidence)
[PR9-R22-09] | Driver Signup UI | Sign Up > Driver | Fields rendered | Incognito, unauthenticated | Pass | 2026-10-22 | QA Tester | 1 | 1 | 100% | Driver form shown with contact/password fields UI only | SPARK-181 (provisional PR9 mapping; verify scope) | 05e2976d (short SHA, source-reported) | EV-UI-OLD · PR9_QA_Traceability_Final.xlsx TEST_CASES; screenshot index in PR9_QA_Final_Report.docx | UserService origin / FE owner-onboarding / Admin auth (UI evidence)
[PR9-R22-10] | Business Signup UI | Sign Up > Business | Business fields rendered | Incognito, unauthenticated | Pass | 2026-10-22 | QA Tester | 1 | 1 | 100% | Name, email, phone, lot type, password fields shown UI only, did not submit | SPARK-181 (provisional PR9 mapping; verify scope) | 05e2976d (short SHA, source-reported) | EV-UI-OLD · PR9_QA_Traceability_Final.xlsx TEST_CASES; screenshot index in PR9_QA_Final_Report.docx | UserService origin / FE owner-onboarding / Admin auth (UI evidence)
[PR9-R22-11] | Business empty-submit | Click Continue to Parking Lot Setup | Required field blocks progression | Blank Business form | Pass | 2026-10-22 | QA Tester | 1 | 1 | 100% | Browser prompt: Vui lòng điền vào trường này Client HTML5 only; no backend submission | SPARK-181 (provisional PR9 mapping; verify scope) | 05e2976d (short SHA, source-reported) | EV-UI-OLD · PR9_QA_Traceability_Final.xlsx TEST_CASES; screenshot index in PR9_QA_Final_Report.docx | UserService origin / FE owner-onboarding / Admin auth (UI evidence)
[PR9-R22-12] | Owner logout | Logout; browser Back; hard refresh | Private dashboard not shown | Owner logged in | Pass | 2026-10-22 | QA Tester | 1 | 1 | 100% | Public Home with Sign In / Sign Up Source result: PASS LIMITED (UI-scope only). UI session only | SPARK-177 (provisional PR9 mapping; verify scope) | 05e2976d (short SHA, source-reported) | EV-LOGOUT-OLD · PR9_QA_Traceability_Final.xlsx TEST_CASES; screenshot index in PR9_QA_Final_Report.docx | UserService origin / FE owner-onboarding / Admin auth (UI evidence)

## SP177_Planned_QA
SMART PARKING ¦ SP177_Planned_QA
Module Code | SP177_Planned_QA
Test requirement | SPARK-177 (Testing task)
Reference Document | 15 planned QA scenarios, none executed in source gap matrix; expected results may need SRS/BA approval.
% Passed of tests | Pass | Fail | Untested | N/A | Number of test cases | Blocked
0% | 0 | 0 | 15 | 0 | 15 | 0
Nguồn: tài liệu gốc trong Historical ZIP. Tổng hợp theo nhiều commit; không suy diễn kết quả ở HEAD mới.
ID | Test Case Description | Test Case Procedure | Expected Results | Inter-test case Dependence | Result | Test date | Tester | Number of tests | Passed | % Passed | Note / Actual | Testing Jira | Baseline commit | Evidence / source | Scenario type
[SP177-OTP-001] | OTP trước 5 phút | Planned only (OTP); prerequisite: QA OTP enabled, controlled clock. Data: OTP từ test fixture; t < 300s | Chấp nhận/không theo quy tắc đã duyệt; log timestamp | QA OTP enabled, controlled clock | Untested |  | QA Tester | 1 | 0 | 0% | NOT EXECUTED. Verify approved SRS/baseline before running. Source status NOT EXECUTED. Do not carry over historical demo/Fix2FA PASS. | SPARK-177 | NOT RUN / NO CURRENT SHA | SPARK177_Acceptance_Gap_Matrix.xlsx!Test chua du bang chung | Auth/OTP · planned QA only
[SP177-OTP-002] | OTP tại ngưỡng đúng 5 phút | Planned only (OTP); prerequisite: QA OTP enabled, controlled clock. Data: t = 300s | Ứng xử ranh giới theo quyết định 06/10, không tự mặc định | QA OTP enabled, controlled clock | Untested |  | QA Tester | 1 | 0 | 0% | NOT EXECUTED. Verify approved SRS/baseline before running. Source status NOT EXECUTED. Do not carry over historical demo/Fix2FA PASS. | SPARK-177 | NOT RUN / NO CURRENT SHA | SPARK177_Acceptance_Gap_Matrix.xlsx!Test chua du bang chung | Auth/OTP · planned QA only
[SP177-OTP-003] | OTP sau 5 phút | Planned only (OTP); prerequisite: QA OTP enabled, controlled clock. Data: t > 300s | OTP hết hạn bị từ chối; status/code theo contract | QA OTP enabled, controlled clock | Untested |  | QA Tester | 1 | 0 | 0% | NOT EXECUTED. Verify approved SRS/baseline before running. Source status NOT EXECUTED. Do not carry over historical demo/Fix2FA PASS. | SPARK-177 | NOT RUN / NO CURRENT SHA | SPARK177_Acceptance_Gap_Matrix.xlsx!Test chua du bang chung | Auth/OTP · planned QA only
[SP177-OTP-004] | Lần xác thực OTP sai thứ 3 | Planned only (OTP); prerequisite: Tài khoản synthetic, clean attempts. Data: 3 lần sai OTP; thử dùng token trước trạng thái lock | Khóa/xử lý theo BR-AUTH đã duyệt; chứng minh trạng thái và token | Tài khoản synthetic, clean attempts | Untested |  | QA Tester | 1 | 0 | 0% | NOT EXECUTED. Verify approved SRS/baseline before running. Source status NOT EXECUTED. Do not carry over historical demo/Fix2FA PASS. | SPARK-177 | NOT RUN / NO CURRENT SHA | SPARK177_Acceptance_Gap_Matrix.xlsx!Test chua du bang chung | Auth/OTP · planned QA only
[SP177-OTP-005] | Mở khóa sau 15 phút | Planned only (OTP); prerequisite: Locked user by approved flow. Data: 14:59, 15:00, 15:01 kiểm thử ranh giới | Chuyển trạng thái theo policy và chặn/gỡ chặn access đúng rule | Locked user by approved flow | Untested |  | QA Tester | 1 | 0 | 0% | NOT EXECUTED. Verify approved SRS/baseline before running. Source status NOT EXECUTED. Do not carry over historical demo/Fix2FA PASS. | SPARK-177 | NOT RUN / NO CURRENT SHA | SPARK177_Acceptance_Gap_Matrix.xlsx!Test chua du bang chung | Auth/OTP · planned QA only
[SP177-JWT-001] | Access token at/beyond expiry | Planned only (Token); prerequisite: Issued token + controlled clock. Data: t exp-1, exp, exp+1 | Access kiểm soát theo JWT expiry và configured tolerance | Issued token + controlled clock | Untested |  | QA Tester | 1 | 0 | 0% | NOT EXECUTED. Verify approved SRS/baseline before running. Source status NOT EXECUTED. Do not carry over historical demo/Fix2FA PASS. | SPARK-177 | NOT RUN / NO CURRENT SHA | SPARK177_Acceptance_Gap_Matrix.xlsx!Test chua du bang chung | Auth/Token · planned QA only
[SP177-REF-001] | Refresh token hết hạn | Planned only (Refresh); prerequisite: Issued refresh token; controlled clock. Data: t exp-1, exp, exp+1 | Refresh hết hạn phải bị từ chối theo approved contract | Issued refresh token; controlled clock | Untested |  | QA Tester | 1 | 0 | 0% | NOT EXECUTED. Verify approved SRS/baseline before running. Source status NOT EXECUTED. Do not carry over historical demo/Fix2FA PASS. | SPARK-177 | NOT RUN / NO CURRENT SHA | SPARK177_Acceptance_Gap_Matrix.xlsx!Test chua du bang chung | Auth/Refresh · planned QA only
[SP177-REF-002] | Refresh sau logout | Planned only (Refresh); prerequisite: Login và giữ refresh trước logout. Data: Dynamic token từ response | Refresh bị revoke theo approved auth policy | Login và giữ refresh trước logout | Untested |  | QA Tester | 1 | 0 | 0% | NOT EXECUTED. Verify approved SRS/baseline before running. Source status NOT EXECUTED. Do not carry over historical demo/Fix2FA PASS. | SPARK-177 | NOT RUN / NO CURRENT SHA | SPARK177_Acceptance_Gap_Matrix.xlsx!Test chua du bang chung | Auth/Refresh · planned QA only
[SP177-REF-003] | Logout + refresh đồng thời | Planned only (Concurrency); prerequisite: Phiên synthetic active. Data: Hai request race với cùng session token | Không còn session trái policy; ghi nhận thứ tự và outcome | Phiên synthetic active | Untested |  | QA Tester | 1 | 0 | 0% | NOT EXECUTED. Verify approved SRS/baseline before running. Source status NOT EXECUTED. Do not carry over historical demo/Fix2FA PASS. | SPARK-177 | NOT RUN / NO CURRENT SHA | SPARK177_Acceptance_Gap_Matrix.xlsx!Test chua du bang chung | Auth/Concurrency · planned QA only
[SP177-JWT-002] | JWT chữ ký bị thay đổi | Planned only (Security); prerequisite: JWT hợp lệ có sẵn từ login. Data: Sửa chữ ký, giữ header/payload format | Bị từ chối, không lọt authorization | JWT hợp lệ có sẵn từ login | Untested |  | QA Tester | 1 | 0 | 0% | NOT EXECUTED. Verify approved SRS/baseline before running. Source status NOT EXECUTED. Do not carry over historical demo/Fix2FA PASS. | SPARK-177 | NOT RUN / NO CURRENT SHA | SPARK177_Acceptance_Gap_Matrix.xlsx!Test chua du bang chung | Auth/Security · planned QA only
[SP177-AUTH-001] | Cross-account token dùng trên account B | Planned only (Authorization); prerequisite: 2 user synthetic A và B. Data: IDs lấy từ registration/response | Không truy cập dữ liệu không được phép theo policy | 2 user synthetic A và B | Untested |  | QA Tester | 1 | 0 | 0% | NOT EXECUTED. Verify approved SRS/baseline before running. Source status NOT EXECUTED. Do not carry over historical demo/Fix2FA PASS. | SPARK-177 | NOT RUN / NO CURRENT SHA | SPARK177_Acceptance_Gap_Matrix.xlsx!Test chua du bang chung | Auth/Authorization · planned QA only
[SP177-AUTH-002] | Permission bị revoke sau khi cấp token | Planned only (Authorization); prerequisite: User role/permission change via authorized test fixture. Data: Old token trước revoke; new token sau revoke | Không còn quyền bị thu hồi trong cửa sổ policy | User role/permission change via authorized test fixture | Untested |  | QA Tester | 1 | 0 | 0% | NOT EXECUTED. Verify approved SRS/baseline before running. Source status NOT EXECUTED. Do not carry over historical demo/Fix2FA PASS. | SPARK-177 | NOT RUN / NO CURRENT SHA | SPARK177_Acceptance_Gap_Matrix.xlsx!Test chua du bang chung | Auth/Authorization · planned QA only
[SP177-AUTH-003] | Disable/lock khi token còn hiệu lực | Planned only (Authorization); prerequisite: User active token issued. Data: Before vs after disable/lock | Token cũ bị xử lý theo security baseline | User active token issued | Untested |  | QA Tester | 1 | 0 | 0% | NOT EXECUTED. Verify approved SRS/baseline before running. Source status NOT EXECUTED. Do not carry over historical demo/Fix2FA PASS. | SPARK-177 | NOT RUN / NO CURRENT SHA | SPARK177_Acceptance_Gap_Matrix.xlsx!Test chua du bang chung | Auth/Authorization · planned QA only
[SP177-MFA-001] | Disable TOTP and re-login | Planned only (MFA); prerequisite: TOTP enabled & verified. Data: Use synthetic account, no real recovery code stored | FE/backend state reflects disabled setting; verify session logic | TOTP enabled & verified | Untested |  | QA Tester | 1 | 0 | 0% | NOT EXECUTED. Verify approved SRS/baseline before running. Source status NOT EXECUTED. Do not carry over historical demo/Fix2FA PASS. | SPARK-177 | NOT RUN / NO CURRENT SHA | SPARK177_Acceptance_Gap_Matrix.xlsx!Test chua du bang chung | Auth/MFA · planned QA only
[SP177-FE-001] | Complete Login→MFA→Logout→Back/Refresh | Planned only (FE UAT); prerequisite: FE build confirmed and QA reviewer named. Data: Browser timestamps and synthetic account | UI access/redirect and revoked token match approved journey | FE build confirmed and QA reviewer named | Untested |  | QA Tester | 1 | 0 | 0% | NOT EXECUTED. Verify approved SRS/baseline before running. Source status NOT EXECUTED. Do not carry over historical demo/Fix2FA PASS. | SPARK-177 | NOT RUN / NO CURRENT SHA | SPARK177_Acceptance_Gap_Matrix.xlsx!Test chua du bang chung | Auth/FE UAT · planned QA only

## Historical_Run_Index
HISTORICAL RUN INDEX
Task / run | Baseline / date | Run type | Reported outcome | QA interpretation | Primary source
SPARK-177 RUN-01 | Demo (old, unknown SHA) | Login/Logout API | 19 PASS; 1 unexecuted; 1 N/A | Historical-only aggregate; not current Fix2FA outcome | SPARK177_QA_Traceability_DRAFT.xlsx / Test runs
SPARK-177 RUN-02 | Fix2FA (unknown SHA) | Manual auth/MFA | 9 PASS / 2 NOT TESTED | Legacy summary only; do not expand to invented cases | SPARK177_QA_Traceability_DRAFT.xlsx / Test runs
SPARK-177 RUN-03 | Fix2FA local | API negative smoke | 5 PASS / 0 FAIL / 0 SKIP | No case-level request/expected/actual in supplied ZIP | SPARK177_QA_Traceability_DRAFT.xlsx / Test runs
SPARK-177 RUN-04 | 2026-10-19 | UserService.Tests | 73 PASS / 0 FAIL / 26 SKIP | Unit run only; 26 integration fixtures skipped | SPARK177_QA_Report_DRAFT.docx
SPARK-177 RUN-05 | 2026-10-19 | MFA exploratory | HTTP200 challenge, 400 invalid format, later 500 | MFA 500 remains an observation; input/challenge validity unverified | SPARK177_QA_Report_DRAFT.docx
SPARK-177 RUN-06 | 2026-10-05 | Historical UAT 20 cases | 8 PASS / 4 FAIL / 1 BLOCKED / 7 NOT TESTED | Different FE baseline, not current UAT | SPARK177_QA_Traceability_DRAFT.xlsx / Test runs
PR9 AUTO-01 | 05e2976d, 2026-10-22 | Developer .NET tests | 167 PASS / 0 FAIL / 0 SKIP | Unit/DI group not counted as QA case | PR9_QA_Final_Report.docx
PR9 FE BUILD | 05e2976d, 2026-10-22 | Frontend build | PASS, 779 modules | Build status only; not E2E | PR9_QA_Final_Report.docx
PR9 E2E / User | 05e2976d, 2026-10-22 | User-root Owner/Admin/FE | 17 detailed case PASS (1 limited UI) | Positive scoped success; not full token/OTP negative signoff | PR9_QA_Traceability_Final.xlsx TEST_CASES
PR9 Facility UI | 05e2976d, 2026-10-22 | Site management UI | 2 UI cases PASS (provisional Facility) | Ownership requires API/call-chain confirmation; recorded in Facility master | PR9_QA_Traceability_Final.xlsx TEST_CASES

## Open_Findings
OPEN FINDINGS
Work / ID | Classification | Source status | Observation | Action / boundary | Evidence
SPARK-177 OBS-MFA-500 | INVESTIGATION | OPEN | MFA login returned HTTP 500 during exploratory test | Validate challenge and TOTP accuracy; no proven Backend bug yet | SPARK177_QA_Report_DRAFT.docx
SPARK-177 ENV-SQL | ENVIRONMENT | BLOCKED | Integration SQL fixture alignment missing | Need approved schema/fixture; 26 unit skips unrelated to case PASS | SPARK177_QA_Traceability_DRAFT.xlsx
SPARK-177 NEWMAN | AC GAP | NOT VERIFIED | Dynamic collection/Newman report absent | Export sanitized Postman collection and execution report before Done | SPARK177_QA_Report_DRAFT.docx
SPARK-177 UAT | AC GAP | NOT VERIFIED | Current FE UAT and reviewer approval absent | Retest on approved baseline; do not carry 05/10 results as current | SPARK177_QA_Report_DRAFT.docx
PR9-R22-16 | QA GAP | NOT RETESTED | Expired/wrong OTP, resend and retry on new FE | Targeted negative coverage after code change | PR9_QA_Traceability_Final.xlsx
PR9-R22-17 | QA GAP | NOT TESTED | Post-logout access/refresh token API invalidation | Do not infer server revocation from Logout UI | PR9_QA_Traceability_Final.xlsx
PR9-R22-18 | REGRESSION GAP | NOT RETESTED | Driver/Operator flow regression outside narrow Owner cycle | Coordinate scope with Leader | PR9_QA_Traceability_Final.xlsx
PR9-SMTP-02 | EXTERNAL ACCOUNT | AUTH 535 FAIL | Shared Gmail refused credential despite TLS | Do not label app defect; alternative SMTP E2E did PASS | PR9_QA_Final_Report.docx
PR9-NEG-01 | OBSERVATION | OBSERVED | Duplicate contact raised AuthException; no full HTTP response | Not PASS until HTTP contract verified | PR9_QA_Traceability_Final.xlsx
PR9-R22-19 | OBSERVATION | NEEDS CLARIFICATION | 20 planned slots vs dashboard physical capacity 0 | Check physical layout definitions; not bug without contract | PR9_QA_Traceability_Final.xlsx
PR9 duplicate handling | MIGRATION RULE | EXCLUDED AGGREGATES | R22-15 aggregates PR9-E2E-01..10; SMTP-01 already covered by E2E | Not double counted | PR9_QA_Traceability_Final.xlsx