## Overview
SMART PARKING ¦ PR #7 — QA DECISION REPORT
Run date | 2026-10-27
PR | https://github.com/Quangthm/Mock-Project-Smart-Parking/pull/7
Jira | SPARK-229 / SPARK-297 (related)
Base / Head | develop / feat/SPARK-229-pricing-calculator
QA branch | qa/SPARK-229-pr7-20261027
Tested commit | fe13d7ce0895786dfcd6906ff81cd6a6edbf023f
PR state | Merged (27 Oct 2026)
QA decision | HOLD / FIX REQUIRED
RESULTS | COUNT
PASS | 60
FAIL | 1
BLOCKED (executed cases) | 0
TOTAL EXECUTED CASES | 61
NOT RUN / E2E WORK | 2
QA VERDICT — Domain & PostgreSQL paths PASS; Reservation JSON contract mismatch reproduced in mock; real E2E not verified.
Evidence scope: local command output supplied by tester; no claims of automated capture or live E2E beyond listed cases.
Next action | Developer fixes enum parsing; QA retests RES-HTTP-03 and relevant regression.
Remaining check | Real ReservationService endpoint + end-to-end accepted snapshot, when supported.

## Test Cases
Case ID | Group | Scenario / Test name | Expected | Actual | Status | Evidence source | Notes
UNIT-01 | Unit / Application | Application.CalculateParkingFeeQueryHandlerTests.Handle_WithPolicyOverride_UsesOverrideWithoutCallingPorts | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-02 | Unit / Application | Application.CalculateParkingFeeQueryHandlerTests.Handle_WithValidReservationId_UsesSnapshotFromPort | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-03 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_05_MidnightCrossing_WithRounding_ShouldRoundHalfUpAtEnd | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-04 | Unit / Application | Application.CalculateParkingFeeQueryHandlerTests.Handle_WithCorruptedOrMissingReservationSnapshot_ThrowsCorruptedPolicySnapshotException_AndNeverCallsTariffPort | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-05 | Unit / Application | Application.CalculateParkingFeeQueryHandlerTests.Handle_WalkInWithActiveTariff_CalculatesSuccessfully | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-06 | Unit / Application | Application.CalculateParkingFeeQueryHandlerTests.Handle_WalkInWithNoActiveTariff_ThrowsTariffNotFoundException | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-07 | Unit / Application | Application.CalculateParkingFeeQueryValidatorTests.Validate_UntrustedCallerProvidingPolicyOverride_FailsValidation | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-08 | Unit / Application | Application.CalculateParkingFeeQueryValidatorTests.Validate_TrustedCallerProvidingPolicyOverride_PassesValidation | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-09 | Unit / Application | Application.CalculateParkingFeeQueryValidatorTests.Validate_WithUnsupportedVehicleType_FailsValidation(vehicleType: "BICYCLE") | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-10 | Unit / Application | Application.CalculateParkingFeeQueryValidatorTests.Validate_WithUnsupportedVehicleType_FailsValidation(vehicleType: "OVERSIZED") | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-11 | Unit / Application | Application.CalculateParkingFeeQueryValidatorTests.Validate_WithUnsupportedVehicleType_FailsValidation(vehicleType: "BUS") | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-12 | Unit / Application | Application.CalculateParkingFeeQueryValidatorTests.Validate_WithUnsupportedVehicleType_FailsValidation(vehicleType: "TRUCK") | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-13 | Unit / Application | Application.CalculateParkingFeeQueryValidatorTests.Validate_WithExitTimeBeforeEntryTime_FailsValidation | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-14 | Unit / Application | Application.CalculateParkingFeeQueryValidatorTests.Validate_WithValidMotorcycleRequest_PassesValidation | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-15 | Unit / Application | Application.CalculateParkingFeeQueryValidatorTests.Validate_WithValidCarRequest_PassesValidation | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-16 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_13_ToSnapshotJson_ContainsRequiredFieldsAndExcludesUnintendedData | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-17 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_06_MultiDayStay_Over48Hours_ShouldCalculateAllDays | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-18 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_08_RoundingMode_CEILING_WHOLE_VND(unrounded: 12, expected: 12) | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-19 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_08_RoundingMode_CEILING_WHOLE_VND(unrounded: 12.1, expected: 13) | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-20 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_08_RoundingMode_CEILING_WHOLE_VND(unrounded: 12.9, expected: 13) | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-21 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_07_RoundingMode_HALF_UP_WHOLE_VND(unrounded: 12.6, expected: 13) | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-22 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_07_RoundingMode_HALF_UP_WHOLE_VND(unrounded: 12.4, expected: 12) | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-23 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_07_RoundingMode_HALF_UP_WHOLE_VND(unrounded: 12.5, expected: 13) | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-24 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_03_StandardDaytime_ShouldChargeAccurately | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-25 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_14_VehicleTypeMismatch_ThrowsPricingDomainException | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-26 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_10_RoundingMode_CEILING_THOUSAND(unrounded: 1001, expected: 2000) | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-27 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_10_RoundingMode_CEILING_THOUSAND(unrounded: 1999, expected: 2000) | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-28 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_10_RoundingMode_CEILING_THOUSAND(unrounded: 1000, expected: 1000) | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-29 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_02_ExactGracePeriod_ShouldBeFree | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-30 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_12_InvalidTimeRange_ThrowsPricingDomainException | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-31 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_04_DayAndEveningBoundaryCrossing_ShouldSplitAndSum | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-32 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_11_ZeroMinutesParked_EntryEqualsExit_ShouldBeZeroFee | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-33 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_09_RoundingMode_HALF_UP_THOUSAND(unrounded: 1500, expected: 2000) | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-34 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_09_RoundingMode_HALF_UP_THOUSAND(unrounded: 1501, expected: 2000) | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-35 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_09_RoundingMode_HALF_UP_THOUSAND(unrounded: 1499, expected: 1000) | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-36 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_09_RoundingMode_HALF_UP_THOUSAND(unrounded: 2500, expected: 3000) | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-37 | Unit / Domain | Domain.ParkingPricingCalculatorTests.TC_PRICE_01_UnderGracePeriod_ShouldBeFree | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-38 | Unit / Integration | Integration.DependencyInjectionTests.ServiceProvider_ShouldResolveAllRequiredDependencies_WithoutExceptions | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-39 | Unit / Persistence | Persistence.TariffPersistenceAdapterTests.GetActivePolicyAsync_WhenTariffIsInactive_ReturnsNull | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-40 | Unit / Persistence | Persistence.TariffPersistenceAdapterTests.GetActivePolicyAsync_WhenTariffExists_ReturnsMappedPricingPolicySnapshot | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-41 | Unit / Persistence | Persistence.TariffPersistenceAdapterTests.GetActivePolicyAsync_WhenNoTariffExists_ReturnsNull | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
UNIT-42 | Unit / Persistence | Persistence.TariffPersistenceAdapterTests.GetActivePolicyAsync_WhenTariffIsSoftDeleted_ReturnsNull | xUnit assertion PASS | Passed | PASS | User log: Step 5 / dotnet test | Release net10.0, SHA fe13d7ce
HTTP-01 | Security | No authorization | 401 | 401 | PASS | User-pasted PowerShell output | Commit fe13d7ce
HTTP-02 | Security | Driver policy override | 400 validation | 400 validation | PASS | User-pasted PowerShell output | Commit fe13d7ce
HTTP-03 | Pricing | Grace period 12 min | 200 / 0 VND | 200 / 0 VND | PASS | User-pasted PowerShell output | Commit fe13d7ce
HTTP-04 | Pricing | Grace period exactly 15 min | 200 / 0 VND | 200 / 0 VND | PASS | User-pasted PowerShell output | Commit fe13d7ce
HTTP-05 | Pricing | Grace exceeded 16 min | 200 / 5,000 VND | 200 / 5,000 VND | PASS | User-pasted PowerShell output | Commit fe13d7ce
HTTP-06 | Pricing | Standard 150 min | 200 / 50,000 VND | 200 / 50,000 VND | PASS | User-pasted PowerShell output | Commit fe13d7ce
HTTP-07 | Pricing | Day/night boundary | 200 / 25,000 VND | 200 / 25,000 VND | PASS | User-pasted PowerShell output | Commit fe13d7ce
HTTP-08 | Pricing | Cross midnight | 200 / 30,000 VND | 200 / 30,000 VND | PASS | User-pasted PowerShell output | Commit fe13d7ce
HTTP-09 | Validation | Exit earlier than entry | 400 validation | 400 validation | PASS | User-pasted PowerShell output | Commit fe13d7ce
HTTP-10 | Validation | Unsupported vehicle BUS | 400 validation | 400 validation | PASS | User-pasted PowerShell output | Commit fe13d7ce
DB-HTTP-01 | PostgreSQL | No active tariff for unknown site | 404 / TARIFF_NOT_FOUND | 404 / TARIFF_NOT_FOUND | PASS | User-pasted PowerShell output | Commit fe13d7ce
DB-HTTP-02 | PostgreSQL | Real DB tariff / 12 min | 200 / 0 VND, version 3 | 200 / 0 VND, version 3 | PASS | User-pasted PowerShell output | Commit fe13d7ce
DB-HTTP-03 | PostgreSQL | Real DB tariff / 16 min | 200 / 5,000 VND, version 3 | 200 / 5,000 VND, version 3 | PASS | User-pasted PowerShell output | Commit fe13d7ce
DB-HTTP-04 | PostgreSQL | Real DB tariff / 150 min | 200 / 50,000 VND, version 3 | 200 / 50,000 VND, version 3 | PASS | User-pasted PowerShell output | Commit fe13d7ce
RES-HTTP-02 | Reservation fault | Connection refused | 503 / RESERVATION_SERVICE_UNAVAILABLE | 503 / RESERVATION_SERVICE_UNAVAILABLE | PASS | User-pasted PowerShell output | Commit fe13d7ce
RES-HTTP-03 | Reservation mock | Valid frozen snapshot, string enums | 200 / 5,000 VND | 422 / CORRUPTED_POLICY_SNAPSHOT | FAIL | User-pasted PowerShell output | Commit fe13d7ce
RES-HTTP-04 | Reservation mock | Snapshot service responds 404 | 422 / CORRUPTED_POLICY_SNAPSHOT | 422 / CORRUPTED_POLICY_SNAPSHOT | PASS | User-pasted PowerShell output | Commit fe13d7ce
RES-HTTP-05 | Reservation mock | Invalid snapshot JSON | 422 / CORRUPTED_POLICY_SNAPSHOT | 422 / CORRUPTED_POLICY_SNAPSHOT | PASS | User-pasted PowerShell output | Commit fe13d7ce
RES-ENUM-CTRL | Reservation mock | Same snapshot, numeric enums (0,2) | 200 / 5,000 VND, version 4 | 200 / 5,000 VND, version 4 | PASS | User-pasted PowerShell output | Commit fe13d7ce

## Bug Report
QA-PR7-001 ¦ Reservation pricing snapshot with string enums fails
Field | Details
Status | REPRODUCED with local HTTP mock; Developer fix needed
Severity | HIGH (proposal; confirm with project lead)
Feature | SPARK-229 / PaymentService → ReservationService snapshot adapter
Commit | fe13d7ce0895786dfcd6906ff81cd6a6edbf023f
Prerequisites | PaymentService in Development; local mock GET endpoint (no real ReservationService)
Steps (short) | POST /api/v1/pricing/calculate with reservationId; mock GET returns valid PricingPolicySnapshot JSON (vehicleType='CAR', roundingMode='HALF_UP_THOUSAND').
Expected | HTTP 200; finalAmountVnd=5000, appliedPolicyVersion=4, appliedTariffId matches
Actual | HTTP 422; errorCode=CORRUPTED_POLICY_SNAPSHOT; RouteMatch=True
Control test | Same JSON except vehicleType=0 and roundingMode=2: HTTP 200, amount=5000, version=4, tariff matches
Impact | Valid reservation frozen tariff may be rejected as corrupted and block checkout/settlement.
Likely cause | Outbound ReadFromJsonAsync<PricingPolicySnapshot>() lacks JSON string-enum converter; ASP.NET MVC converter does not automatically apply to HttpClient.
Fix direction | Align shared JSON serialization options for snapshot contract. Add string-enum regression test at HTTP adapter layer. Do not change dev source in QA branch.
Retest | String-enum valid 200; numeric compatibility as contract allows; missing/invalid JSON 422; vehicleType/site checks; real ReservationService E2E when available.
Source: adapter | https://github.com/Quangthm/Mock-Project-Smart-Parking/blob/fe13d7ce0895786dfcd6906ff81cd6a6edbf023f/src/Services/PaymentService/SmartParking.PaymentService.Infrastructure/Adapters/Outbound/ReservationSnapshotHttpAdapter.cs
Source: model | https://github.com/Quangthm/Mock-Project-Smart-Parking/blob/fe13d7ce0895786dfcd6906ff81cd6a6edbf023f/src/Services/PaymentService/SmartParking.PaymentService.Domain/Pricing/PricingModels.cs
Source: contract | https://github.com/Quangthm/Mock-Project-Smart-Parking/blob/fe13d7ce0895786dfcd6906ff81cd6a6edbf023f/docs/02-architecture/api/payment-service/01-pricing-calculation.contract.md

## Evidence & Gaps
EVIDENCE INDEX ¦ EXECUTION LOGS AND LIMITATIONS
Ref | Source | Observation / extract | Classification | Result | Follow-up
EV-01 | User uploaded test log (27/10/2026) | Test Run Successful; Total tests: 42; Passed: 42; Build succeeded 0 warnings/errors | Unit | PASS | Available in conversation attachment
EV-02 | User PowerShell output / Step 6 | HTTP-01..HTTP-10: PASS=10 FAIL=0; values and HTTP status matched | HTTP smoke | PASS | Development auth stub, not gateway auth
EV-03 | User PowerShell output / Step 8-R1 | DB-HTTP-01: 404 / TARIFF_NOT_FOUND | Real PostgreSQL negative | PASS | DB connected
EV-04 | User PowerShell output / Step 9 | RES-HTTP-02: 503 / RESERVATION_SERVICE_UNAVAILABLE | Fault injection | PASS | Connection refused
EV-05 | User PowerShell output / Step 8-R1 | RES-HTTP-01: expected 503, actual 504 / RESERVATION_SERVICE_TIMEOUT | Diagnostic, incorrect initial test oracle | NOT COUNTED | Different timeout branch; not product bug
EV-06 | User PowerShell output / Step 10-R1 | DB-HTTP-02..04: 3 PASS; 0/5000/50000 VND; version=3; TariffMatch=True | Real PostgreSQL positive | PASS | Fixture deleted: 0 temporary rows
EV-07 | User PowerShell output / Step 11 | RES-HTTP-03: 422/CORRUPTED_POLICY_SNAPSHOT for valid string enums; RouteMatch=True | Reservation mock positive | FAIL | QA-PR7-001
EV-08 | User PowerShell output / Step 11 | RES-HTTP-04 and RES-HTTP-05: 422 / CORRUPTED_POLICY_SNAPSHOT | Reservation mock negative | PASS | No tariff fallback observed
EV-09 | User PowerShell output / Step 11-R1 | Numeric enums: RouteMatch=True, HTTP 200, amount=5000, version=4, tariff match | Controlled A/B validation | PASS | Confirms string-enum interoperability problem
EV-10 | User PowerShell output / Steps 10-R1, 11-R1 | API & DB stopped; QA cleanup PASS; Git clean on SHA fe13d7ce | Cleanup / safety | PASS | No QA data left
GAP-01 | Step 11 local grep (keyword-based) | No matching ReservationService pricing-snapshot route text found | Real-service E2E | NOT RUN | Not proof of absent endpoint; need owner/environment confirmation
GAP-02 | Current test coverage | No E2E with real accepted_pricing_snapshot source after actual booking | Real reservation frozen tariff | NOT RUN | Test after endpoint + data are available