## Cover
SMARTPARK • USERSERVICE TEST REPORT | SPARK-201 template v1.0 / PR #14
Document status | No PR14 cases executed for this service; NOT approved / reviewer pending
Prepared | 2026-10-27 • QA execution log; reviewer and signoff pending
Baseline | PR #14 merged into develop; Jira SPARK-247 / SPARK-249 / SPARK-250; SPARK-201 format is review-ready (not officially adopted)
Code snapshot | Merge SHA 5995394ef27c789cdd2cedc0d256e85d23d7e411 ¦ PaymentService net10.0 ¦ FE Vite 8.3.1
Service owner rule | Each test recorded under its first/backend root caller; downstream dependencies are referenced, not duplicated
Execution | 0 service-owned cases: 0 Pass, 0 Fail, 0 Blocked, 0 Not Run
Reusable case rule | No cross-service duplication; FR/BR/US/UC not guessed; unverified mappings labelled for reviewer
Coverage note | Unit tests are QA rerun of developer-authored assertions; PostgreSQL/mock cases separately identified
Evidence / frontend | Frontend-only homepage tests are tracked in central Word QA report, not allocated to a backend service.
Release gate | Not sign-off; Payment webhook FAIL; E2E not verified. Evidence refs are local console/session notes, not committed links.
Original format | Adapted directly from uploaded SPARK-201 Tester-Workbook-v1.0.xlsx: all 7 original tabs retained.

## Cases
Test ID | Title | FR / requirement | BR | US | UC | API | Jira | Type / dimension | Risk | Preconditions | Data / setup | Steps | Independent expected result | Actual result | Evidence links | Status | Defect links | Retest / prior run links | Tester | Executed UTC | Baseline / readiness

## Test Report
Metric | Value | Interpretation
Total cases | 0 | Only Cases of this owning service; FE-only evidence not counted
Pass | 0 | Executed cases marked Pass; unit runs reflect developer assertions
Fail | 0 | Expected-vs-actual mismatch, pending triage
Blocked | 0 | Dependency / integration unavailable; not a Pass
Not Run | 0 | Not executed; no invented results
N/A | 0 | Non-applicability only after approval
Pass rate | n/a | Pass / (Pass + Fail), not a release acceptance score
Execution coverage | n/a | (Pass + Fail) / (Total − N/A), not complete E2E
Run / build | PR14 merged SHA 5995394ef27c / 2026-10-27 / QA mock + local PostgreSQL | Record code, schema, FE and environment versions
Evidence report | Source mapping / local QA run context; no live service execution | Attach sanitized report and defect links
Sign-off | PENDING — service not signed off | Use Adoption & Signoff; this report is not acceptance

## Test Case List
Test ID | Title | Jira | Execution location | Readiness

## Case Template
Test ID | Title | FR / requirement | BR | US | UC | API | Jira | Type / dimension | Risk | Preconditions | Data / setup | Steps | Independent expected result | Actual result | Evidence links | Status | Defect links | Retest / prior run links | Tester | Executed UTC | Baseline / readiness
TEMPLATE-001 | Replace with one independently decidable behavior | FR-ID + version/clause | BR-ID or N/A + reason | US-ID | UC-ID | Method/path + design version | SPARK-xxx | API / Integration / UAT + dimension | High / Medium / Low | Authentication/state/dependencies | Synthetic fixture and generated IDs | 1. Action 2. Read back state | Independent approved result; include no forbidden side effects |  |  | Not Run |  |  |  |  | Authority / C-A-X-F / dependency

## Review Checklist
Check ID | Review area | Required evidence | Yes / No / N/A | Case / test / gap links | Reviewer / date
UNIT-01 | Business assertions | Expected outcome derived independently; return and state checked
UNIT-02 | Branches | Success, rejection, missing/null, cancellation, failure
UNIT-03 | Controlled clock | Exact equality boundaries; no sleeps
UNIT-04 | Meaningful mocks | Do not mock rule under test; forbidden save/message asserted
UNIT-05 | Isolation | No order/shared-state dependence; repeatable fixtures
UNIT-06 | Mutation/state | Change a key condition/state update: test must fail; inspect rollback
UNIT-07 | Coverage gaps | Uncovered rules recorded; mocks do not replace DB/concurrency tests
EDGE-01 | Happy path | Case IDs and evidence, or reviewed N/A; blocked needs dependency link
EDGE-02 | Negative input | Case IDs and evidence, or reviewed N/A; blocked needs dependency link
EDGE-03 | Boundary below/equal/above | Case IDs and evidence, or reviewed N/A; blocked needs dependency link
EDGE-04 | Authorization and foreign scope | Case IDs and evidence, or reviewed N/A; blocked needs dependency link
EDGE-05 | Current-state revocation | Case IDs and evidence, or reviewed N/A; blocked needs dependency link
EDGE-06 | State transitions | Case IDs and evidence, or reviewed N/A; blocked needs dependency link
EDGE-07 | Retry/idempotency | Case IDs and evidence, or reviewed N/A; blocked needs dependency link
EDGE-08 | Concurrent race | Case IDs and evidence, or reviewed N/A; blocked needs dependency link
EDGE-09 | Dependency failure/unknown outcome | Case IDs and evidence, or reviewed N/A; blocked needs dependency link
EDGE-10 | Persistence/rollback | Case IDs and evidence, or reviewed N/A; blocked needs dependency link
EDGE-11 | Secret leakage | Case IDs and evidence, or reviewed N/A; blocked needs dependency link
EDGE-12 | Cleanup | Case IDs and evidence, or reviewed N/A; blocked needs dependency link

## Adoption & Signoff
Task / run | Case IDs / package version | Execution / defect evidence | Unit + edge review | UAT reviewer / evidence | Decision / conditions / date
PR14 / UserService | No cases in scope | No execution evidence supplied | Not reviewed | Not applicable to this PR run | Pending; not an approval